## Manual
Task to be completed | Date expected to complete
Wheel to Motor Couplers | 20/09/13
Main Structure | 21/09/13
Main Hand | 23/09/13
Shooting Hand | 25/09/13
Motor Drivers | 22/09/13
Power Controller for Shooter | 25/09/13
Power Unit | 22/09/13
Encoders | 21/09/13
Wireless Module | 26/09/13
Testing | 27 -29/09/13
List is based on priority level

## Autonomous
Task to be completed | Date Expected to complete
Cutter | 22/09/13
Sensor Panel Power Management Unit | 24/09/13
Battery Charge Controller | 25/09/13
Finding Batteries | 25/09/13
Testing | 26-29/09/13

## General
Task to be completed | Date expected to complete
IML Allocation | 24/09/13
Path Creation | 26/09/13